# project management plan

# for the

# SMART MENU MANAGMENT

# SMM

# 30/10/2021

Team Members:

Team Member 1: Mayar Ashraf 192785

Team Member 2: Aya Hesham 203022

Team Member 3: Salma Mahmoud 202235

Team Member 4: Habiba Adel 201696

Table of Contents:

Section	Page

SECTION 1.  OVERVIEW	1

1.1 Project Summary	1

1.1.1 Purpose, Scope, and Objectives	1

1.1.2 Assumptions and Constraints	3

1.1.3 Project Deliverables	5

SECTION 4. PROJECT ORGANIZATION	6

SECION 5. MANAGEment PROCESS	7

5.1 Start-up	7

5.1.1 Estimation	8

5.2 Work Planning	25

5.2.1 Work Activities	25

5.2.2 Scheduling Requirements ………………………………………………………………………………….37

5.2.3 Resource Allocation	41

5.4  Risk Managment....................................................................................................... 42

SecTION 6.  TECHNICAL PROCESS	26

6.2 Methods, Tools and Techniques	9

6.3 Project Infrastructure	11

# SECTION 1.  OVERVIEW

## Project Summary

The current system is a smart menu ordering system that allows the customer to choose their orders from the menu and then the order is sent automatically to the restaurant and it begins to prepare the order. Furthermore, our system provides the customers to reserve a table with or without order by specifying the time/date of the reservation also the customers have the option to pay by cash or by credit card.

### Purpose, Scope, and Objectives

Purpose:

The purpose of the system is to make the ordering and reservation easier to the customer and to also help the customer that are nervous to interact with people feel more comfortable and eat delicious food with no worries. Additionally, the system will help the customer to review and rate each dish and staff with no embarrassment, and these reviews and rates will help the staff to improve and the chefs take in consideration those rates to improve the dishes with customer preferences.

Scope:

Our smart menu gives detailed description on each dish to help the customer know the ingredients added in case of any allergies. In addition, the customer can search by ingredients, certain price, and category to help them browse faster through the menu. Our stakeholders are manager, receptionist, customer, cleaner, waiter, and head chief.

- Manager: evaluates dishes rate and service rate.

- Receptionist: send confirmation messages for reservation.

- Customer: orders meal, rates each dish and service, and reserve a table.

- Cleaner: receive messages from customer to clean the table.

- Waiter: sends confirmation messages for the order.

- Head chief: receives the customer’s order to start preparing.

System Functionality:

- Login/Sign up: the system requires from the customer to login and signup by phone number.

- Orders a meal: the system must give access to the customer to order a meal from any list.

- Reserve a table: the system gives access to the customer to reserve a table before arriving to the restaurant and must choose number of people and time slot, and can also choose to order a meal before arriving or not.

- Categorize list:  the system must categorize each dish to different list.

- Search dishes: the system should have search by category, certain ingredients, price.

- Display receipt: the system must display the receipt including taxes.

- Display price: the system must show the price on each dish.

- Display Time: the system should give access to the staff to view the time remaining to complete the required order after the customer checks out.

- Rate food: The system must have a rating poll for every dish and reviews should be seen on every dish.

- Rate service: the system must give access to the customer to the rate the service.

- Edit order: the system should give access to the customer to edit his or her order.

- Hide dishes: the system should give access to the staff to hide unavailable dishes.

- Receive order:  the system must send the orders to the staff to start preparing the order.

Objectives:

  - The customer will save time to reserve and to order,

  - In addition, the customer will save time to pay since paying with credit/debit card is available.

  - Regarding the pandemic, social distancing is required and the system will help in considering these COVID regulations as much as possible.

  - Since our system is a website, we reduce paper use which will save the environment.

### Assumptions and Constraints

Assumptions:

System assumptions:

- User have cellular data.

- User know how to scan the QR code.

- User can read English or Arabic.

- User have a working phone number to log in/sign up.

- The system will be available for 12 hours a day.

- The system supports 500 user per hour.

- The system can provide 3 seconds or less response time to display the menu.

- The manager must hide the dishes that are unavailable to avoid confusion.

Managerial assumptions:

- The team can involve the client if he/she needs to or understands in a certain phase in the system.

- The system can have some changes regarding any phase to work properly.

- The system can have additional techniques if needed.

- Office hours can be changed in case of system overload.

- Certain training can be added if the clients want a technique that the staff lack.

Constraints:

System constraints:

-    The user should login/sign up by his/her phone number.

-    The user should receive a code to confirm his/her phone number to view the menu.

-     The system must view the time remaining to the customer for each order.

-     The customer must rate the dishes and the service.

- The system should secure private information regarding the payment process by visa/debit card.

- The system should have error rate of users submitting wrong payment details must not exceed 12 percent.

Managerial constraints:

- The system must be submitted at 30/12/2021.

- The system must not exceed the $4000 budget.

- The system must be done on the suggested tools only.

- The system must have a weekly report submitted from the team.

- The system must be connected to a banking system for visa/debit card.

- Any required change the developer suggests the client must know before working on it.

### 1.1.3	Project Deliverables

Phase 1:  project proposal (30/10/2021)

Phase 2:  (1/11/2021 – 25/11/2021)

- Analysis Phase:

- Requirement Gathering:   1/11/2021

- Requirements Analysis: 4/11/2021

- Requirements Validation:   4/11/2021

- Software Requirements Specification Documents:5/11/2021

- Design Phase:

- Wireframes: 8/11/2021

- Class Diagram: 10/11/2021

- Use Case Diagram: 11/11/2021

- Context Diagram: 12/11/2021

- Implementation Phase:

- Execution:14/11/2021

- Monitoring: 16/11/2021

- Control: 16/11/2021

- Production: 17/11/2021

- Testing Phase:

- Test plan: 18/11/2021

- Test execution report: 20/11/2021

- Analyzing results: 22/11/2021

- Time estimation report: 25/11/2021

Final Phase: (1/12/2021)

# SECTION 4. PROJECT ORGANIZATION

4.3 Project Roles and Responsibilities

Habiba Adel

(Implementation Manager)

Salma Mahmoud

(Design Manager)

Aya Hesham

(Analysis Manager)

Mayar Ashraf

(Project Manager)

Mayar Ashraf

(Testing Manager)

Project Manager:

The project manager’s responsibilities are:

- must organize schedule for each phase with the deadlines that should be submitted at.

- must divide each responsibility to each manager.

- if possible, give more directional steps on how to manage each phase.

- must schedule meeting each week to check on the development of each phase and to answer any concerns regarding the responsibility each manager has.

- must be available for any questions needed for the project.

- should have a presentation showing the other managers the risks, budget, and tools needed to complete the project.

Analysis Manager:

The analysis manager’s responsibilities are:

- train and recruit employees.

- design and build technical processes to address business issues.

- Build, develop, and maintain data models.

- Deliver analytical reports.

- Examine and interpret results of analytical reports for stakeholders.

Design Manager:

The design manager’s responsibilities are:

- Motivate the design team.

- Ensure the designs and drawings are completed on time.

- Maintain documentation of the design process.

- Reduce financial risk during the process.

- Design use case diagram and context diagram to show what each user will perform in the system.

- Make sure the diagrams are how the client want and need in the system.

- Help the design team with any obstacle they face.

Implementation Manager:

The implementation manager’s responsibilities are:

- Choose developers team for implementation.

- Plan detailed plan of how the software should function.

- Divide the work on the implementation team to turn the diagrams into well-developed website the user can use easily.

- Make a Graphical User Interface so the client can visualize how the system will work.

- Make sure the team is working on the plan and support the team with any challenges they face.

Testing Manager:

The testing manager’s responsibilities are:

- Organize the testing process.

- Manage the technical team.

- Make sure the team uses high quality tools to test the system.

- Ensure to deliver high quality system to the clients.

- Take in consideration the risks that the clients will face in case of any malfunction.

SECION 5. management Process

5.1 Start-up:

5.1.1 Estimation:

Source for language weight [https://www.qsm.com/resources/function-point-languages-table]

Aya Hesham 203022:

Size Estimation:

Function Point:

Payment Function

Scenario:

When the customer makes his/her order, s/he should pay for it. So, s/he clicks on the make payment button. This event will call the make payment function that has two options paying cash or paying by a credit card. If the customer chooses the cash option, a message will appear to the customer informing him/her to go to the casher to pay for his/her order. If the customer chooses the payment method as credit card, the payment method will be saved in the database in the Payment table as a credit card method, and a new page with the total amount will appear to make the user enter the information of the credit card. After entering the data, a message will appear that the payment has been done successfully or an error message in case the entered data is not valid.

.

Count of components:

1.External input types (EI): (4 components)

-Card number

-Holder name

-Expiry date

-CVV

2. External output types (EO): (1 component)

- A message to inform the user his/her payment has done successfully / Error, check your data and re-enter them again.

3. External inquiry types (Queries) (EQ): (4 components)

-Checks if the entered data is valid or not.

-Insert payment method as visa in the payment table in the database.

-Insert order status as paid in the order table in the database.

4. Logical internal file types (ILF): (2 components)

-Payment table

-Order table

5. External interface files (UI): (1 component)

-Banking system

Data types, Record types, and Complexity:

1. External input types (EI):

-Data types: 4 (Card number, Holder name, Expiry date, and CVV)

-Record types: 2 (Payment table, Order table)

-Complexity:  Low

2. External output types (EO):

-Data types: 1(Feedback message)

-Record types: 0

-Complexity: Low

3. External inquiry types (Queries) (EQ):

-Data types: 4 (one check and three insertions)

-Record types: 2 (Payment table, Order table)

-Complexity:  Low

4. Logical internal file types (LIF):

-Data types: 4 (Card number, Holder name, Expiry date, and CVV)

-Record types: 2 (Payment table, Order table)

-Complexity:  Low

5. External interface files (UI):

-Data types: 4 (Card number, Holder name, Expiry date, and CVV)

-Record types: 1 (Holder table)

-Complexity:  Low

Size estimation:

(3*3) + (1*4) + (4*3) + (4*7) + (4*5) = 73 FP

73 FP * 47(JavaScript) = 3431 LOC / 1000 = 3.431 KLOC

Albrecht II function point:

Categorize List Function:

Scenario:

In order to facilitate the search function, each dish should be assigned to its category list, and the staff are responsible for this function.

Each categorize list function consists of dish name, dish price, dish description, and the staff will select the category name from the category list. After adding the dish information, a message will appear to the staff member to inform him/her that the dish has been added successfully to the menu or an error has been occurred.

1.Inputs: (4 inputs)

-Dish name

-dish price

-dish description

-category name

2.Outputs: (1 output)

-The dish has been added successfully/an error has been occurred.

3.Entities (Storage): (3 entities)

-Item table

-Menu table

-Category enumeration

Size estimation: 𝐹𝑝 𝑐𝑜𝑢𝑛𝑡 = 𝑁i ∗ 0.58 + 𝑁e ∗ 1.66 + 𝑁o ∗ 0.26

= (4*0.58) + (3 * 1.66) + (1 * 0.26) = 7.56 FP

= 7.56 FP * 47(JavaScript) = 355.32 LOC / 1000   = 0.35532 KLOC

Effort Estimation:

COCOMO II: A (size)sf * (product of exponent multipliers)

- Exponent driver ratings:

- Precedentedness (PREC): Low (4.96)

-The project has been developed many times so, it’s like many projects in the business labor.

- Development Flexibility (FLEX): Very high (1.01)

-There is only one way to categorize the dishes (through the website).

- Architecture / Risk reduction (RESL): Nominal (4.24)

-The main requirements are almost known as the system is not unique.

- Team cohesion (TEAM):  Extra high (0.00)

-The team members work at the same office in the same city, so the communication is so easy.

- Process maturity (PMAT): High (3.12)

-The function is well organized and well structured.

sf = B + 0.01 * Σ (exponent driver ratings), where B is a constant value = 0.91

= 0.91 + 0.01 * (4.96 + 1.01 + 4.24 + 0.00 + 3.12)

- Exponent multipliers:

- Product reliability & complexity (RCPX): Nominal (1.00)

-The function’s reliability is high, the product complexity is very high, and the database size is moderate.

- Required reusability (RUSE): Low (0.95)

-The function cannot be reused in the system to assign the staff members to their jobs but with some modifications in code.

- Platform difficulty (PDIF): Low (0.87)

-The function is designed to be user friendly for the staff members, the user interface of the function is written in simple language to be easily understood.

- Personnel capability (PERS): Nominal (1.00)

-The analyst’s capability for the function is nominal, the programmer capability for the function is nominal, and the personnel continuity is nominal too (3+3+3 = 9)

- Personnel experience (PREX): High (0.87)

-The application experience and platform experience are nominal, but the language experience and tool experience are high which makes the overall personnel experience for this function high.

- Facilities available (FCIL): Nominal (1.00)

-The use of software tools support and multisite conditions in the function are nominal (6).

- Schedule pressure (SCED): Low (1.14)

-The function is not critical (85% of nominal).

Effort = A (size)sf * (product of exponent multipliers), where A is a constant = 2.94

= 2.94 (0.35532)1.0433 * (1.00 * 0.95*0.87*1.00*0.87*1.00*1.14)

= 0.81879612 PM

Salma Mahmoud 202235:

Size Estimation:

Function point:

Reserve table:

Scenario:

This function is used by clients to reserve tables they simply enter to the info of the reservation such as the phone number, number of people, number of tables and E-mail address and after entering the info mentioned above, they simply click submit, then the details of the reservation appear to the customer.

Reserve a table:

- External Input: 4

1-phone number

2-number of people

3-number of tables

4-E-mail address

- External Output: 2

1-the user’s reservation details

2-your reservation has been done successfully

- External Inquiry: 1

1-Insert the reservation into the database

- Logical internal File: 2

1-Reserve table

2-customer table

- External Interface: 0

Identify data types, record types and complexity:

- External input (EI): 4

-4 data types: phone number, number of people, number of tables, E-mail address

-1 record type: user input

-low complexity

- External output (EO): 2

-2 data type: the user’s reservation details; your reservation has been done successfully

-1 record type: reservation table

-low complexity

- External Inquiry (EQ):  4

-4data types: phone number, number of people, number of tables, E-mail address

-1 record type: customer table, reservation table

-low complexity

- Logical internal File (LIF): 4

-4data types: phone number, number of people, number of tables, E-mail address

-1 record type: customer table, reservation table

-low complexity

- External Interface (EIF):

-0 datatype

-0 record type

-low complexity

Multiplier:

External input types (EI): 3

External output types (EO): 4

External Query types (EQ): 3

Logical internal file types (LIF): 7

External interface file types (EIF): 5

Size Estimation:

(4*3) +(2*4) +(1*3) +(2*7) +(0*5) = 37 FP

37 * 47(JavaScript) =1739 LOC/1000

= 1.739KLOC

Function Search Dishes size estimation (Using Albrecht II method):

Function Scenario:

User clicks on the search bar and then enters the desire dishes name and then they click search on the search bar button, after clicking on the search button the database views the desired dish name using the select query. User will select his/her specific dish to reserve it then a confirmation message will appear to the user with their order details.

Inputs:

1-Dish name

Output:

1-confirmation message

Entities (storage):

1-Item table

2-Menu table

Size estimation:

Ni * 0.58 + Ne*1.66 + No*0.26

1*0.58+1*1.66+2*0.26=2.76FP

2.76 FP * (47) =129.72LOC =0.12972 KLOC

Effort Estimation:

COCOMO 81:

Reserve a table:

Effort = C (size)^k

Reserve table function will use a semi-detached system because it has some constraints regarding the phone number and e-mail address.

C = 3.0

K= 1.12

Effort=3.0(1.739) ^1.12=5.57 PM

COCOMO II:

Search dishes:

Effort (PM) = A (Size)^sf x (Product of exponent multipliers)

A = 2.94

Sf= B +0.01* estimation (exponent driver ratings)

B= 0.91

Estimation (exponent driver ratings) = 5 factors (PREC +FLEX+RESL+TEAM+PMAT)

1-PREC: Low 4.96

-Justification:  low because it is not unique, it can be used in another system with small changes.

2-FLEX: high 2.48

Justification:  high because the function is flexible and simply anyone can use it.

3-RESL: very low 6.20

Justification:  there is no risk in case something wrong happens

4-TEAM: very high 1.24

Justification: the team is a close small team

5-PMAT: very high 1.24

Justification: the function is well organized a simple to use

4.96+2.48+6.20+1.24+1.24=16.12

SF=0.91+0.01*16.12=1.0712

Product of exponent multipliers:

1-RCPX: low 0.83

Justification: low because it is simple to use, but the product complexity is very complex and the database size is also very large

2-RUSE: very low non

Justification: it can’t be RUSE

3-PDIF: low 0.87

Justification: platform difficulty is not difficult so it is low and the time and storage constraint is also low 50%

4-PERS: low 1.26

Justification: the personal capability is low and the Applications, Platform, Language and Tool Experience is also low '9months'

5-PREX: low 1.12

Justification: the personal experience is low and the Applications, Platform, Language and Tool Experience is also low '9months'

6-FCIL: very low 1.30

Justification: it is low because it didn't use software tools

7-SCED: very low 1.43

Justification: the function is small and didn’t need a schedule pressure.

Product of exponent multipliers=0.83*0.87*1.26*1.12*1.30*1.43=1.894

Effort=2.94(0.12972) ^ 1.0712*1.894=0.6245

Habiba Adel 201696:

Size Estimation:

Function Point:

Rate food: When a customer finishes his or her meal and checks out and fills all the required data for the payment, a function called rate food will appear to the customer. Rate food a 5-star rating, 1(very bad) to 5 (excellent), and comment feedback on how the food and the test was. This function will help our restaurant in improving the food and the test of it, it will give instructions to our chef on how to improve the food to be more delices, in the other hand it will help our chiefs to be more motivated with the good comments and rating and this will help them feel more open to working and make more good food.

Rate service function will include the order of the customer and a 5-star rating each. The customer will rate the food, write a comment in the comment box provided, and write his/her number to send a thank you message to our chiefs.

Count of components:

- External Input types (EI): 3

- Star rating

- Comment

- E-mail

- External Output types (EO): 1

- “Thank you” message

- External Inquiry types (EQ): 2

- Check if the phone number exists or not

- Insert the rating and feedback in the database

- Logical internal file types (LIF): 2

- Menu table

- Customer table

- External Interface file types (EIF): 0

Identify Datatypes, Record Types and Complexity:

EI:

- 3 data types: Star rating, feedback comment, Phone number

- 1 record type: User input

- Low complexity

EO:

- 1 data type: message sent to the customer

- 1 record type: menu table

- Low complexity

EQ:

- 3 data types: Star rating, Comment, Phone number

- 2 record type: customer table, menu table

- Low complexity

LIF:

- 3 data types: Star rating, Comment, Phone number

- 2 record type: customer table, menu table

- Low complexity

EIF:

- 0 datatype

- 0 record type

- Low complexity

Size estimation = 3*3 +1*4+ 2*3 +2*7+ 0*5 = 33 FP

Language used: JavaScript

33 FP * 47 = 1551LOC = 1.551 KLOC

Albrecht II function

Edit order: if the customer wants to edit the order to cancel something or to add some items again so it will be easy for the customer to add and to cancel an unwanted item.

Edit order is function includes the following: menu to re-order what they want and also to cancel unwanted dishes

Count of components:

Inputs: 5

- Click on edit order button

- Click on the unwanted or wanted dishes

- Continue button

- Select payment method that will use it

- Confirmation button

Outputs: 2

- Confirmation message

- New order will be sent to the staff

Entities (Storage): 2

- Staff table (to know the new order)

- Menu table

Size Estimation: Ni * 0.58 + Ne*1.66 + No*0.26

5*0.58 + 2*1.66 + 2*0.26 = 6.74 FP

Language used: JavaScript

6.74 FP * 47 = 316.78 LOC = 0.31678 KLOC

Effort Estimation:

COCOMO 81:

Rate Food:

Effort = C (size)^k

C= organic system (2.4)

K= 1.05

Effort = 2.4(1.551 KLOC) ^1.05 = 2.640228571 KLOC

COCOMO II:

Edit order:

Effort (PM) = A (Size)^SF x (Product of exponent multipliers)

A = 2.94

Sf= B +0.01* estimation (exponent driver ratings)

B= 0.91

Estimation (exponent driver ratings) = 5 factors (PREC +FLEX+RESL+TEAM+PMAT)

1-      PREC:  low 4.96

2-      FLEX: nominal 3.04

3-      RESL: High 2.83

4-      TEAM: extra high 0.00

5-      PMAT: very low 7.80

4.96+3.04+2.83+0+7.80= 18.63

Sf = 0.91 + (0.01*18.63) = 1.0963

Product of exponent multipliers:

Product:

-           RELY:  1.10 (High) “high financial loss”

-          DATA: 1 (Nominal) “10 D / P < 100”

-          DOCU: 1.23 (Very high) “Very excess save for lifecycle needs”

-          CPLX: 0.87 (low)

-          REUSE: 1 (nominal) “across project”

Computer:

-          TIME: 1.11 (High) “because the system is 70% use of available time”

-          STOR: 1.00 (Nominal) “because the system uses less than 50% use of available storage”

-          PVOL: 0.87 (Low) “because major change every 12 months, minor change every 1 months”

Personnel:

-          ACAP: 1 (Nominal) “55th percentile”

-          AEXP: 1.22 (Very low) “LESS THAN OR EQUAL 2 MONTHES “

-          PCAP:1.15 (Low) “35th percentile”

-          PEXP: 1.09 (low) “6 months”

-          LEXP: 0.91 (High)” 3 years”

-          PCON: 1.00 (Nominal) “12% / year”

Project:

-          TOOL: 1.00 (Nominal)” basic lifecycle”

-          SITE: 1.09 (Low)” Multi-city and multi-company”

-          SCED: 1.00 (Nominal) “100%”

Product of exponent multipliers =

1.10*1*1.23*0.87*1*1.11*1*0.87*1*1.22*1.15*1.09*0.91*1*1*1.09*1 =2.8100

Effort = 2.94(0.31678) ^1.0963*(2.8100) = 2.342795 KLOC

Mayar Ashraf 192785:

Size Estimation:

Function Point:

Rate Service:

When a customer finishes his or her meal and checks out and fills all the required data for the payment, a function called rate service will appear to the customer. Rate service a 5-star rating, 1(very bad) to 5 (very good), and comment feedback on how was the service and staff during their night in our restaurant. This function will help our restaurant in improving the service and will give instructions to our staff on how to treat our customer in a better way and in a more civilized way; and also, it will help our staff to be more motivated with the good comments and rating and this will help them feel more open to working.

Rate service function will include staff names attached with a picture and a 5-star rating each. The customer will rate the staff that was in charge of the customer’s evening, write a comment in the comment box provided, and write his/her number to send a thank you message.

Count of components:

- External Input types (EI): 3

- Star rating

- Comment

- Phone number

- External Output types (EO): 1

- Thank you, message

- External Inquiry types (EQ): 2

- Check if the phone number exists or not

- Insert the rating and feedback in the database

- Logical internal file types (LIF): 2

- Staff table

- Customer table

- External Interface file types (EIF): 0

Identify Datatypes, Record Types and Complexity:

EI:

- 3 data types: Star rating, Comment, Phone number

- 1 record type: User input

- Low complexity

EO:

- 1 data type: message sent to the customer

- 1 record type: staff table

- Low complexity

EQ:

- 3 data types: Star rating, Comment, Phone number

- 2 record type: customer table, staff table

- Low complexity

LIF:

- 3 data types: Star rating, Comment, Phone number

- 2 record type: customer table, staff table

- Low complexity

EIF:

- 0 datatype

- 0 record type

- Low complexity

Size estimation = 3*3 +1*4+ 2*3 +2*7+ 0*5 = 33 FP

Language used: JavaScript

33 FP * (47) = 1551 LOC = 1.551 KLOC

Albrecht II Function point:

Hide dishes:

The staff has some privileges in our system one of them is hiding the dishes that are no longer available in the kitchen or had a low rating due to customer’s review. Hide dish’s function is important in our restaurant because it minimizes the customer’s confusion regarding whether this specific dish is available or not.

Hide dish’s function includes the following: staff must click on the dish he/she needs to hide from the menu, enters a code to complete the process, and clicks on yes to confirm the operation.

Count of components:

Inputs: (4)

- Click on hide dish button

- Click on the unwanted dish

- Enter a code (known by the staff only)

- Continue button (to hide the dish)

Outputs: (2)

- Confirmation message

- Dish will be unavailable to the customer

Entities (Storage): (3)

- Staff table (to check if the code is correct or not)

- Item Table

- Menu table

Size Estimation: Ni * 0.58 + Ne*1.66 + No*0.26

4*0.58 + 3*1.66 + 2*0.26 = 7.82 FP

Language used: JavaScript

7.82 FP * (47) = 367.54 LOC = 0.36754 KLOC

Effort Estimation:

COCOMO 81:

Rate Service:

The rate service is a simple function with no constraints so using organic system will be more suitable.

Effort = C (size)^k

C= 2.4

K= 1.05

Effort = 2.4(1.551) ^1.05 = 3.8049 PM

COCOMO II:

Hide dishes:

Effort (PM) = A (Size)^sf x (Product of exponent multipliers)

A = 2.94

Sf= B +0.01* estimation (exponent driver ratings)

B= 0.91

Estimation (exponent driver ratings) = 5 factors (PREC +FLEX+RESL+TEAM+PMAT)

- PREC: very high 1.24

(Most features are understandable objectives, working with related software systems, little need of new hardware and operational procedures)

- FLEX: low 4.05

(Some functions need a pre-established requirement, and little need of external interface specification)

- RESL: Nominal 4.24

(Number and critically of risk items 1, 80% of required top software architects available to project)

- TEAM: very high 1.10

(Strong consistency of stakeholders’ objectives and cultures, considerable experience of stakeholders in operating as a team)

- PMAT: Extra high 0.00

1.24 + 4.05+4.24+ 1.10+ 0.00 = 10.63

Sf = 0.91 + 0.01*10.63 = 1.0163

Product of exponent multipliers:

Product:

- RELY:  Nominal 1.00

(Hide dishes function has a moderate reliability and can easily recover from losses)

- DATA: High 1.14

(Assume that our database size is 170,000 bytes and the program size is 367.54 so 170,000/367.54 = 462.534 which is 100 <= D/P<1000)

- DOCU: High 1.11

(Hide dishes function depends on life cycle since it’s a daily use function)

- CPLX:  Very low 0.73

(The hide function won’t need any complex code instead a simple if conditions and simple read and write statements)

- REUSE: Very High 1.15

(Hide dishes is a construct function that will be needed across product line)

Computer:

- TIME: Nominal 1.00

(This function will need less than 50% of execution time)

- STOR: Very high 1.17

(Hide dishes uses the main storage to hide some data in the database for all users)

- PVOL: Low 0.87

(This function will not have any major changes since it will have the same functionality)

Personnel:

- ACAP: Nominal 1.00

(This function needs the level of experience of analyst is 55th percentile)

- ALEXP: Very high 0.81

(The level of the project team in this function is experienced for over 6 years)

- PCAP: Very high 0.76

(This function needs the capability of the programmers as a team is 90th percentile depending on the ability and efficiency of the team)

- PEXP: Nominal 1.00

(This function needs the programmers to have at least 1 year experience in graphic user interface)

- LEXP: High 0.91

(This function needs the programmer to have at least 3year experience in language and tools)

- PCON: Nominal 1.00

(This function will need annual personnel turnover from 12%/year)

Project:

- TOOL: Very high 0.78

(This function will rely on very strong active life cycle methods)

- SITE: High 0.93

(This function will need a wideband electronic communication)

- SCED: Nominal 1.00

(This function will need 100% schedule constraint on the project team)

Product of exponent multipliers = 1.00*1.14*1.11*0.73*1.15*1*1.17*0.87*0.71*0.81*0.76*1.00*0.91*1.00*0.78*0.93*1.00 = 0.31198

Effort = 2.94(0.36754) ^ 1.0518 * 0.31198= 0.32008 PM

5.2 Work Planning:

5.2.1 Work Activities:

- Analysis Phase: [Aya 203022]

Product Breakdown Structure:

- Design Phase: [Salma 202235]

Product Breakdown Structure:

- Implementation Phase: [Habiba 201696]

Product Breakdown Structure:

- Testing Phase: [Mayar 192785]

Product Breakdown Structure:

    - Scheduling Requirements:

Precedence Table:

Gantt Chart:

- Analysis Phase: [Aya 203022]

CPM Scheduling:

Critical Path 1: (in red) 4,6,9,13,14,16

Critical Path 2: (in red) 4,6,9,13,14,17

- Design Phase: [Salma 202235]

CPM Scheduling:

Critical Path 1: (in red) 20,21,22,24,25

Critical Path 2: (in red) 20,21,27,29

Critical Path 3: (in red) 20,21,27,30

Critical Path 4: (in red) 20,21,27,31

- Implementation Phase: [Habiba 201696]

CPM Scheduling:

Critical Path: (in red) 36,41,44,45

- Testing Phase: [Mayar 192785]

CPM Scheduling:

Critical Path: (in red) 48, 50, 54, 57, 60, 64

    - Resource Allocation:

- Analysis Phase: [Aya 203022]

Resources:

Human resources:

- 5 Employees

- 2,000 EGP / each

Material resources:

- 50 papers

- 10 coloured pens

- 5 pencils

- 5 erasers

- 1,000 EGP material/ weekly

Food resources:

- 20 water bottles

- 20 cups of coffee

- 1,000 EGP food/ weekly

Physical resources:

- 5pcs

- 1 WIFI access point

- 1,000 EGP internet package/monthly

- Design Phase: [Salma 202235]

Resources:

Human Resources:

- 10 Employees

- 2,000 EGP/each

Material Resources:

- 50 papers

- 10 coloured pens

- 10 pencils

- 10 erasers

- 3 Apps (12 EGP/monthly)

- 1,000 material/weekly

Physical Resources:

- 10 pcs

- 1WIFI access point

- 1,000 EGP internet package /monthly

- Implementation Phase: [Habiba 201696]

Resources:

Human Resources:

- 10 employees

- 4,000 EGP/each

Material Resources:

- 3 Apps (100 EGP/monthly)

Physical Resources:

- 10 pcs

- 1 server

- 1 WIFI access point

- 1,000 EGP internet package /monthly

- Testing Phase: [Mayar 192785]

Resources:

Human Resources:

- 5 employees

- 4,000 EGP/each

Material Resources:

- 2 Apps (100 EGP/each)

Physical Resources:

- 5 pcs

- 1 server

- 1 WIFI access point

- 1,000 EGP internet package /each

Cost Estimation:

5(2,000) +70(1,000) +40(1,000) +1,000+10(2,000) +80(1,000) +3(12) +1,000+10(4,000) +3(100) +1,000+5(4,000) +2(100) +1,000 = 284536 EGP

5.4 Risk Management:

- Analysis Phase: [Aya 203022]

Risks:

Generic Risk: 2

1-	Project team member leaving:

Risk Identification: The probability of employee turnover while working on a project is low (5%). The time of finding a new member to replace the old one’s skills, expertise and project background is estimated as 15 days:

Risk likelihood: Percentage of project team member leaving   5% = 0.05 Before Resolution

Risk impact: delay in time    15 days.

Exposure to data loss = Risk likelihood * Risk impact

0.05 * 15 = 0.75 days.

2-	Stakeholders’ issues:

Risk Identification: The probability that the stakeholders have low engagements, give inaccurate expectations, change their needs is high. It may reach 80%. The cost of changing the requirements, the diagrams, and the implemented functions in cost of rebuilding the project estimated at 50,000 L.E.:

Risk likelihood: Percentage of changing needs 80% = 0.8 Before Resolution

Risk impact: Loss in cost    50,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.8 * 50,000 = 40,000 L.E.

Specific Risk: 3

- Incomplete requirements :

Risk Identification: The probability of the requirements that are incomplete leading to deliverables that are unstable, unusable or are generally unacceptable is 50% chance of happening which is a significant probability level. The time of completing the requirements estimated at 3 days:

Risk likelihood: Percentage of loss   50% = 0.5 Before Resolution

Risk impact: Loss in days     3 days.

Exposure to data loss = Risk likelihood * Risk impact

0.5 * 3 = 1.5 days

- Undocumented requirements:

Risk Identification: The probability of missing requirements to be documented after finishing the analysis phase is a moderate percentage. As it equals to 15%. The cost of  adding the missing requirements, designing them, implementing and testing them is measured in the cost of rebuilding is estimated at 15,000 L.E.:

Risk likelihood: Percentage of loss   15% = 0.15 Before Resolution

Risk impact: Loss in cost		       15,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

= 0.15 * 15,000 = 2,250 L.E.

- Infeasible requirements:

Risk Identification: The probability of having requirements that go well beyond the capabilities of the system is 30% which is considered a significant probability level. The impact will be estimated in cost equals to 200,000 L.E above budgeted expenditure.

Risk likelihood: Percentage of loss   30% = 0.3 Before Resolution

Risk impact: Loss in cost    200,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.3 * 200,000 = 60,000 L.E.

Contingency plan: This risk can be mitigated with a quick feasibility or cost assessment. This solution reduces the risk to 5%. The impact will be estimated in cost equals to 33,333 L.E above budgeted expenditure.

Risk likelihood: Percentage of loss   5% = 0.05 After Resolution

Risk impact: Loss in cost    33,333 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.05 * 33,333 = 1,666.65 L.E.

Cost of Risk Reduction 2,500 L.E.

Risk Reduction Leverage = (Risk Exposure Before – Risk Exposure After) / Cost of Risk Reduction

= (60,000 – 33,333) /2,500 = 10.6668

- Design Phase: [Salma 202235]

Generic Risk: 2

1-communication risk

2-Gather questionnaire

Specific Risk: 3

3- User interface design, delay of process in designing could happen so it affects the whole project.

4-Make a design that violet the legal requirements of the projects

5-failure in database and lost some information and that may lead to repeat or modify the database.

Risk identification:

Risk management is the process of recognizing, monitoring, and managing any threats that could have an impact on a project's overall health and reputation. Therefore, the team must identify the risk very quickly to know how to solve it properly.

Risk Analysis:

1-communication risk

Risk Identification: When you are in control of a project, you must keep to a strong work ethic of effective and timely communication. Members of a team may overlook important aspects of good communication from time to time.

Risk likelihood: Percentage of loss   10% = 0.1

Risk impact: loss in cost 17000L.E

Exposure to data loss = Risk likelihood * Risk impact

0.1*17000=1700L.E

2-Gather questionnaire

Risk Identification: if the questionnaires are not distributed or gathered correctly the results may be inaccurate and lead to incorrect design issues down the line in later phases which may cause delays and going over budget

Risk likelihood: Percentage of loss   20% = 0.2

Risk impact: loss in cost 2000L.E

Exposure to data loss = Risk likelihood * Risk impact

0.2*2000=400L.E

3-user interface design

Risk Identification: while implementation, the designer can make any mistake that may affect the implementation process.

Risk likelihood: Percentage of loss   10% = 0.1

Risk impact: loss in cost 2500L.E

Exposure to data loss = Risk likelihood * Risk impact

0.1*2500=250L.E

4- Make a design that violet the legal requirements of the projects

Risk Identification: As for every projects, there are some legal obligations that the developer cannot ignore and these will require additional time, effort and money to correct it.

Risk likelihood: Percentage of loss   25% = 0.25

Risk impact: loss in cost 22000L.E

Exposure to data loss = Risk likelihood * Risk impact

0.25*22000=5500L.E

Contingency plan: the solution for such risk is to taking advice from professional designers on how to follow legal requirements and to make sure that every member of the team is follow these requirements, this reduces the risk to 5% and the method will cost 1500L.E:

Risk likelihood: Percentage of loss   5% = 0.05

Risk impact: loss in cost 1500L.E

Exposure to data loss = Risk likelihood * Risk impact

0.05*1500=75L.E

Cost of Risk Reduction 1500 L.E.

Risk Reduction Leverage = (Risk Exposure Before – Risk Exposure After) / Cost of Risk Reduction

= (5500 – 75) / 1500 =3.6166

5-Failure in database

Risk Identification: a conflict between user research and stakeholders occurs during the preparation of the schematic version, causing a delay because it is possible that some problems would arise when building the system.

Risk likelihood: Percentage of loss   20% = 0.2

Risk impact: loss in cost 15000L.E

Exposure to data loss = Risk likelihood * Risk impact

0.2*15000=3000L.E

Contingency plan: the solution for this risk is to choose the appropriate elements for the system without causing problems with it and also can reduces the errors by analyzes the user's requirements, this reduces the risk to 10% and the method will cost 4000L.E

Risk likelihood: Percentage of loss   10% = 0.1

Risk impact: loss in cost 4000L.E

Exposure to data loss = Risk likelihood * Risk impact

0.1*4000=400L.E

Cost of Risk Reduction 2500 L.E.

Risk Reduction Leverage = (Risk Exposure Before – Risk Exposure After) / Cost of Risk Reduction

= (3000 – 400) / 2500 =1.04

- Implementation Phase: [Habiba 201696]

Risks:

Generic Risk: 2

- Some programmers are absent due to illness. This will very certainly create a delay in the project's completion. As the project is being carried out, there is a significant risk of this happening. COVID-19 makes the staff sick. The operation will cost about 80,000 with a probability of 30%:

Risk Exposure = 80,000 * 0.3 = 24,000

Avoiding the delay in the project:

By Managing Online Meetings and Online Delivering, the work can be done online to                      prevent face-to-face meetings and to overcome the epidemic with the least amount of time lost, that could reduce that risk occurring to 20% and will cost 30,000:

Risk Exposure = 30,000 * 0.2 = 6,000

RRL= (RE before – RE after) / (risk reduction cost)

RRL= (24,000 – 6,000) / 5,000   = 3.6

Specific Risk: 3

- Software development is code of poor quality. Due to hasty effort and a variety of other causes, projects may contain low-quality code. Bugs, logical flaws, and other issues with code are all possible. That operation will cost 300,000 with probability of 20%:

- Risk Exposure = 300,000 * 0.2 = 60,000

- To avoid this problem, you must test code frequently and resolving bugs and logical errors when they found, and all development know standards coding for the system to use it. that could reduce that risk occurring to 30% and will cost 100,000.

- Risk Exposure = 100,000 * 0.3 = 30,000

RRL= (60,000 – 30,000) / 20,000   = 1.5

- The SQL developer recognized that the ERD diagram provided for database implementation is incorrect. As a result, it must be redone which will cause a delay. the probability of loss is 30% and caused a loss of 350,000.

- Risk Exposure = 350,000 * 0.3 = 105,000

To avoid this problem, the manager must check for every step happened before the next step will be done and a new ERD diagram will done, and it will cost 50,000 and probability of reduce 10%

Risk Exposure = 50,000 * 0.1 = 5,000

RRL= (105,000 – 5,000) / 40,000   = 2.5

- Smart menu software system: The software system is highly sophisticated and advanced which is divided into many subsystems such as (IT, Management, Maintenance, etc.…) with a GUI for each subsystem and high security measures. The probability of a risk occurring is 30% and the loss of it on the implementation phase is 70,000:

- Risk Exposure: 70,000 * 0.3 = 21,000

- Avoiding such a risk according to the implementation plan which the implementation manager has put together. The plan would decrease the risk to 4% and the cost by 30,000.

Risk Exposure after contingency plan:

Risk Exposure =30,000*0.04=1,200

Risk Reduction Leverage

RRL = (21,000-1,200) / 3,000 =6.6

- Testing Phase: [Mayar 192785]

Risks:

Generic Risk: 2

- Sharing the work on unsecured app

- Malfunction in PC without saving the work

Specific Risk: 3

- While testing, errors appear and can lead to unknown error that affect a certain function in our Smart Menu website.

- Since Stress testing is very critical some functions could not run-on different scenarios which will lead in changing some line of codes with the implementation team and in delaying the submission to the client.

- When calculating the results for the testing could lead to confusion since different testing techniques are being used and many test cases are being submitted.

Risk identification: Testing phase can lead to many risks that could cost the whole project to fail. In general, risks are the situations that lead to defects that was not taken into our consideration. Testing team have different testing types that help in reducing the risks that they would face; for example, Unit testing tests each function alone to specify the error faster and help the other function not to be exposure to that error.

Risk Analysis: (numbered according to risks section above)

- Sharing the work on unsecured app:

Risk Identification: The probability losing the data while sharing is 10%. The cost of losing in cost of rebuilding it estimated at 15,0000 L.E.:

Risk likelihood: Percentage of loss   10% = 0.1 Before Resolution

Risk impact: Loss in cost     15,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.1 * 15,000 = 1500 L.E.

- Malfunction in PC without saving the work:

Risk Identification: The probability losing the data while sharing is 15%. The cost of losing in cost of rebuilding it estimated at 17,0000 L.E.:

Risk likelihood: Percentage of loss   15% = 0.15 Before Resolution

Risk impact: Loss in cost    17,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.15 * 17,000 = 2550 L.E.

- Unknown Errors Risk:

Risk Identification: The probability of unknown error risk that could lead to malfunction in the whole project is 20%. The cost of changing some functions is measured in cost of rebuilding it estimated at 20,000 L.E.:

Risk likelihood: Percentage of loss   20% = 0.2 Before Resolution

Risk impact: Loss in cost    20,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.2 * 20,000 = 4000 L.E.

- Stress Testing Risk:

Risk Identification: The probability of changing some line of codes when Stress testing is 25%. The cost of changing some functions is measured in cost of rebuilding it estimated at 25,000 L.E.:

Risk likelihood: Percentage of loss   25% = 0.25 Before Resolution

Risk impact: Loss in cost		       25,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.25 * 25,000 = 6250 L.E.

Contingency plan: The solution for such risk is to test while implementing each function to reduce the risk of changing any line of codes. This reduces the risk to 6%. The impact will reduce since rebuilding will lessen. Estimated by cost 20,000 L.E.

Risk likelihood: Percentage of loss   6% = 0.06 After Resolution

Risk impact: Loss in cost		       20,000 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.06 * 20,000 = 1200 L.E.

Cost of Risk Reduction 2500 L.E.

Risk Reduction Leverage = (Risk Exposure Before – Risk Exposure After) / Cost of Risk Reduction

= (6250 – 1200) / 2500 =2.02

- Calculating Execution test cases:

Risk Identification: The probability of confusion happening in calculating the number of test cases is 6%. The impact will be calculated in cost, the confusion is estimated at 9,300 L.E.:

Risk likelihood: Percentage of loss   6% = 0.06 Before Resolution

Risk impact: Loss in cost    9,300 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.06 * 9,300 = 558 L.E.

Contingency plan: The solution for such risk is to write last updated date on each test case. This reduces the risk to 3%. The impact will be calculated in cost, the confusion reduced so the impact estimated at 7,300 L.E.:

Risk likelihood: Percentage of loss   3% = 0.03 After Resolution

Risk impact: Loss in cost    7,300 L.E.

Exposure to data loss = Risk likelihood * Risk impact

0.03 * 7,300 = 219 L.E.

Cost of Risk Reduction 500 L.E.

Risk Reduction Leverage = (Risk Exposure Before – Risk Exposure After) / Cost of Risk Reduction

= (9300 – 7300) / 500 = 4

# SecTION 6.  TECHNICAL PROCESS

## 6.2	Methods, Tools and Techniques

Methods:

SDM Methodology:

Agile development is the right approach to software development and project management that helps deliver value to our customers faster. For our system, smart menu, sometimes we can have some changes depending on either customers’ feedback and rating or the change of market price that will lead to slight changes in our system to correspond with the real world. Regarding these previous reasons, Agile development will help in those changes to be done easily with no time wasted and with minimal cost.

SPM Methodology:

PMBOK, Project Management Body of Knowledge, offers testing techniques and evidence-based practices guaranteeing what our team is doing and how. In addition, it will be an accurate approach to our project management since it will eliminate all unnecessary processes. The PMBOK will enhance project manager abilities to be organized and improved. Moreover, the PMBOK method refers to five process steps which are initiating, planning, executing, controlling, and closing and it contains many techniques that could help widen and improve our smart menu system.

Tools:

Analysis Phase Tools:

- Documentation and requirements: Microsoft word document

Design Phase Tools:

- Wireframes: Canva

- Class diagram, Use case diagram, Context diagram: draw.io

Implementation Phase Tools:

Frontend tools:

- Html/CSS/JavaScript code: Brackets

Backend tools:

- Java code: NetBeans

- SQL code: Microsoft SQL server Management studio

Testing Phase Tools:

- Test web application: Browser Stack

Others:

- QR code generator: qrcodeMonkey

Techniques:

We will be using the following languages in our system:

Frontend Techniques:

- HTML: It’s the fundamental coding language that creates and organizes a web content.

- CSS: It’s used to style the HTML elements of the web pages. It’s used to define layouts, colors, and fonts.

- JavaScript: It’s used to make the elements of the webpages more interactive, and make the website dynamic.

Backend Techniques:

- Java language: It's used to develop desktop and mobile apps, as well as big data processing and embedded systems. It is also simple to use and has clear structure to programs and allows code to be reused.

- SQL: our system will need database to save all staffs’ information username, password, email, etc. and more data regarding our users. So, SQL language will help us develop a useful database to store and manage data.

## 6.3	Project Infrastructure

Our system will be a website since the customer will scan the QR code and it will guide it to a website, while the manager and staff will already be logged in to the website with their username and password to use the system and be connected with the customer.

User:

Required system: Smart phone with 5MP camera resolution or more

Operating System: Android or IOS

Hardware:

- High-definition display

- 4 GB RAM or more

- 1.8 GHZ dual one processor

More requirements: Internet connection, QR code scanner app if the OS doesn't support scanning by the camera application.

Developer:

Required system: PC, Server, banking system, TP-Link Router

Operating System: Windows or macOS

Hardware:

- Intel core i7.

- 25 MB cache memory.

- 32 GB RAM or more.

- 8mps Internet connection.